## Executive Dashboard
Project 03 — IT BA Project: Software Feature Specification
Intelligent Order Modification & Cancellation System
Project Name | Intelligent Order Modification & Cancellation System
Company | UrbanThread (Simulated)
Project Type | IT BA — Software Feature Specification
Status | Complete
Disclaimer | This is a student portfolio project. All company details, metrics, stakeholder interviews, user data, and business context are simulated / fictional unless explicitly stated otherwise. No real client work or production data is represented.
Summary Metrics
Total Business Requirements | 12
Total Functional Requirements | 18
Total Non-Functional Requirements | 10
Total User Stories | 24
Total Acceptance Criteria | 35+
Total Use Cases | 8
Total UAT Scenarios | 30
Total Risks | 10
Total Assumptions | 10
Total Dependencies | 10

## Stakeholder Matrix
ID | Stakeholder | Role | Interest | Influence | Engagement Strategy
STK-001 | VP of Customer Experience | Executive Sponsor | High | High | Manage closely; weekly updates
STK-002 | Head of Customer Support | Business Owner | High | High | Collaborate; requirements validation
STK-003 | Product Manager | Product Owner | High | High | Daily collaboration; backlog prioritization
STK-004 | Engineering Lead | Technical Lead | Medium | High | Consult on feasibility; technical review
STK-005 | UX Designer | Design Lead | High | Medium | Collaborate on wireframes; usability
STK-006 | QA Lead | Testing Lead | Medium | Medium | Consult on test scenarios
STK-007 | Finance Manager | Payment/Refund Stakeholder | Medium | Medium | Consult on refund rules
STK-008 | Warehouse Operations Manager | Fulfillment Stakeholder | High | Medium | Consult on inventory release timing
STK-009 | Customer Support Agents | End Users (Internal) | High | Low | Inform; gather feedback
STK-010 | Customers | End Users (External) | High | Low | Represent via personas; usability testing
STK-011 | Legal/Compliance | Compliance | Low | Medium | Consult on policy requirements
STK-012 | Data/Analytics Team | Reporting | Medium | Low | Consult on KPI tracking

## Business Requirements
BR ID | Requirement | Rationale / Business Value | Priority | Source
BR-001 | The system shall enable customers to self-serve order modifications and cancellations without contacting support. | Reduces support burden; improves customer experience. | Must Have | STK-001, STK-002
BR-002 | The system shall apply consistent, codified business rules to determine order modification and cancellation eligibility. | Ensures fair and consistent customer treatment; reduces errors. | Must Have | STK-002
BR-003 | The system shall process eligible modification and cancellation requests in real-time (within 2 minutes). | Improves customer satisfaction; reduces wait times. | Must Have | STK-001
BR-004 | The system shall automatically release inventory for cancelled items to enable reallocation. | Reduces unnecessary shipping costs; improves inventory efficiency. | Must Have | STK-008
BR-005 | The system shall automatically process payment adjustments (refunds or payment method updates) for eligible changes. | Reduces manual finance work; improves customer trust. | Must Have | STK-007
BR-006 | The system shall send automated notifications to customers at each stage of the modification/cancellation process. | Keeps customers informed; reduces follow-up contacts. | Must Have | STK-001
BR-007 | The system shall maintain a comprehensive audit trail of all modification and cancellation actions. | Supports compliance; enables dispute resolution. | Should Have | STK-011
BR-008 | The system shall provide support agents with visibility into customer self-service actions for context. | Enables effective exception handling; improves support efficiency. | Should Have | STK-002
BR-009 | The system shall provide operational reporting on modification/cancellation volumes, success rates, and processing times. | Enables continuous improvement; supports KPI tracking. | Should Have | STK-001, STK-012
BR-010 | The system shall handle peak volumes (up to 3x normal) without degradation in performance. | Ensures reliability during high-demand periods. | Should Have | STK-004
BR-011 | The system shall comply with applicable data protection and payment card industry (PCI) requirements. | Legal and regulatory compliance. | Must Have | STK-011
BR-012 | The system shall reduce support contacts related to order changes by at least 40% within 6 months of launch. | Measurable business outcome; justifies investment. | Must Have | STK-001

## Functional Requirements
FR ID | Requirement | Rationale / Business Value | Priority | Source | Traces to BR
FR-001 | The system shall display a "Modify Order" and "Cancel Order" option on the order details page for eligible orders. | Provides entry point for self-service. | Must Have | STK-001 | BR-001
FR-002 | The system shall evaluate order eligibility for modification and cancellation in real-time based on order status, fulfillment stage, and business rules. | Ensures only eligible orders can be changed. | Must Have | STK-002 | BR-002
FR-003 | The system shall display the specific reason when an order is not eligible for modification or cancellation. | Provides transparency; reduces confusion. | Must Have | STK-001 | BR-001
FR-004 | The system shall allow customers to modify the delivery address for eligible orders. | Addresses common modification need. | Must Have | STK-001 | BR-001
FR-005 | The system shall allow customers to change the shipping speed (standard to express or express to standard) for eligible orders. | Addresses common modification need; potential revenue impact. | Should Have | STK-001 | BR-001
FR-006 | The system shall allow customers to cancel individual items within a multi-item order if eligible. | Provides flexibility; reduces full-order cancellations. | Should Have | STK-001 | BR-001
FR-007 | The system shall allow customers to cancel an entire order if eligible. | Core self-service capability. | Must Have | STK-001 | BR-001
FR-008 | The system shall calculate and display any applicable fees, refunds, or payment adjustments before the customer confirms the action. | Transparency; reduces disputes. | Must Have | STK-007 | BR-005
FR-009 | The system shall require customer confirmation before processing any modification or cancellation. | Prevents accidental changes. | Must Have | STK-001 | BR-001
FR-010 | The system shall update the Order Management System (OMS) with the modification or cancellation in real-time. | Ensures order data accuracy. | Must Have | STK-004 | BR-002
FR-011 | The system shall trigger inventory release in the Warehouse Management System (WMS) for cancelled items. | Enables inventory reallocation. | Must Have | STK-008 | BR-004
FR-012 | The system shall trigger payment adjustment (refund or payment method update) through the payment gateway. | Automates financial reconciliation. | Must Have | STK-007 | BR-005
FR-013 | The system shall send an email confirmation to the customer upon successful modification or cancellation. | Keeps customer informed. | Must Have | STK-001 | BR-006
FR-014 | The system shall send an SMS notification to the customer upon successful modification or cancellation (if opted in). | Provides real-time updates. | Should Have | STK-001 | BR-006
FR-015 | The system shall send a push notification to the customer upon successful modification or cancellation (if app installed). | Provides real-time updates. | Should Have | STK-001 | BR-006
FR-016 | The system shall log all modification and cancellation actions with timestamp, user ID, action type, and before/after values. | Supports audit and compliance. | Should Have | STK-011 | BR-007
FR-017 | The system shall provide a read-only view of customer self-service actions in the support agent dashboard. | Enables context for exception handling. | Should Have | STK-002 | BR-008
FR-018 | The system shall generate operational reports on modification/cancellation metrics (volume, success rate, processing time, reasons). | Supports continuous improvement. | Should Have | STK-012 | BR-009

## Non-Functional Requirements
NFR ID | Requirement | Rationale / Business Value | Priority | Source | Traces to BR
NFR-001 | The system shall evaluate eligibility and display options within 3 seconds of the customer initiating a request (95th percentile). | Ensures responsive experience. | Must Have | STK-004 | BR-003
NFR-002 | The system shall process a confirmed modification or cancellation within 60 seconds (95th percentile). | Ensures timely completion. | Must Have | STK-004 | BR-003
NFR-003 | The system shall support up to 500 concurrent modification/cancellation requests without degradation. | Handles peak volumes. | Should Have | STK-004 | BR-010
NFR-004 | The system shall be available 99.9% of the time (excluding planned maintenance). | Ensures reliability. | Must Have | STK-004 | BR-001
NFR-005 | The system shall encrypt all data in transit (TLS 1.2+) and at rest (AES-256). | Security compliance. | Must Have | STK-011 | BR-011
NFR-006 | The system shall comply with PCI DSS requirements for payment data handling. | Regulatory compliance. | Must Have | STK-011 | BR-011
NFR-007 | The system shall be accessible via web (Chrome, Firefox, Safari, Edge) and mobile (iOS 14+, Android 10+). | Broad accessibility. | Must Have | STK-005 | BR-001
NFR-008 | The system shall meet WCAG 2.1 AA accessibility standards. | Inclusive design. | Should Have | STK-005 | BR-001
NFR-009 | The system shall provide clear, actionable error messages to users in plain language. | Usability; reduces frustration. | Must Have | STK-005 | BR-001
NFR-010 | The system shall log all errors and exceptions for debugging and monitoring. | Operational visibility. | Should Have | STK-004 | BR-009

## User Stories
US ID | User Story | Priority | Traces to FR
US-001 | As a customer, I want to see if my order is eligible for modification or cancellation, so that I know my options without contacting support. | Must Have | FR-001, FR-002
US-002 | As a customer, I want to understand why my order is not eligible for modification or cancellation, so that I understand the limitation. | Must Have | FR-003
US-003 | As a customer, I want to change my delivery address on an eligible order, so that my order goes to the correct location. | Must Have | FR-004
US-004 | As a customer, I want to change my shipping speed on an eligible order, so that I can receive my order faster or slower. | Should Have | FR-005
US-005 | As a customer, I want to cancel individual items in my order, so that I can remove items I no longer want. | Should Have | FR-006
US-006 | As a customer, I want to cancel my entire order, so that I can get a full refund. | Must Have | FR-007
US-007 | As a customer, I want to see any fees or refunds before confirming my change, so that I understand the financial impact. | Must Have | FR-008
US-008 | As a customer, I want to confirm my change before it is processed, so that I don't make accidental changes. | Must Have | FR-009
US-009 | As a customer, I want to receive a confirmation email after my change is processed, so that I have a record of the change. | Must Have | FR-013
US-010 | As a customer, I want to receive an SMS notification after my change is processed, so that I know immediately. | Should Have | FR-014
US-011 | As a customer, I want to receive a push notification after my change is processed, so that I know immediately. | Should Have | FR-015
US-012 | As a customer, I want to see the updated order status after my change, so that I know the change was successful. | Must Have | FR-010
US-013 | As a support agent, I want to see what self-service actions a customer has taken, so that I can provide informed support. | Should Have | FR-017
US-014 | As a support agent, I want to view the audit trail of changes, so that I can resolve disputes. | Should Have | FR-016
US-015 | As a support agent, I want to handle exception cases that cannot be self-served, so that I can resolve complex issues. | Must Have | FR-003
US-016 | As a support manager, I want to see reports on modification/cancellation volumes and success rates, so that I can monitor performance. | Should Have | FR-018
US-017 | As a support manager, I want to see the reasons for ineligibility, so that I can identify process improvements. | Could Have | FR-003, FR-018
US-018 | As a finance manager, I want to see refund processing reports, so that I can reconcile payments. | Should Have | FR-012, FR-018
US-019 | As a warehouse manager, I want to see inventory release reports, so that I can plan operations. | Should Have | FR-011, FR-018
US-020 | As a compliance officer, I want to access audit logs, so that I can ensure regulatory compliance. | Should Have | FR-016
US-021 | As a system, I want to validate order eligibility in real-time, so that only eligible orders are modified. | Must Have | FR-002
US-022 | As a system, I want to handle concurrent modification requests gracefully, so that data integrity is maintained. | Must Have | FR-002, FR-010
US-023 | As a system, I want to retry failed payment adjustments, so that refunds are processed reliably. | Should Have | FR-012
US-024 | As a system, I want to notify administrators of integration failures, so that issues are resolved quickly. | Should Have | FR-011, FR-012

## Acceptance Criteria
AC ID | User Story | Criteria | Type
AC-001 | US-001 | Given a customer is logged in and views an order that is eligible for modification, When the order details page loads, Then the system shall display "Modify Order" and "Cancel Order" buttons. | Positive
AC-002 | US-001 | Given a customer is logged in and views an order that is not eligible for modification, When the order details page loads, Then the system shall display a message stating "This order can no longer be modified or cancelled." | Negative
AC-003 | US-001 | Given a customer is logged in and views an order that is partially eligible, When the order details page loads, Then the system shall display "Cancel Order" only for eligible items. | Boundary
AC-004 | US-002 | Given an order is not eligible for cancellation, When the customer selects "Cancel Order", Then the system shall display the reason: "This order has already been shipped and cannot be cancelled." | Positive
AC-005 | US-002 | Given an order is not eligible for modification, When the customer attempts to modify the delivery address, Then the system shall prevent the action and display: "Delivery address cannot be changed once the order is being prepared for shipment." | Negative
AC-006 | US-003 | Given an order is eligible for address modification, When the customer enters a new valid address and confirms, Then the system shall update the delivery address in the OMS and display a success message. | Positive
AC-007 | US-003 | Given an order is eligible for address modification, When the customer enters an invalid address, Then the system shall display a validation error and prevent submission. | Negative
AC-008 | US-003 | Given an order is eligible for address modification, When the customer enters an address outside the serviceable area, Then the system shall display: "We do not currently deliver to this address." | Boundary
AC-009 | US-006 | Given an order is eligible for cancellation, When the customer confirms cancellation, Then the system shall cancel the order, initiate a refund, release inventory, and send a confirmation email. | Positive
AC-010 | US-006 | Given an order is not eligible for cancellation, When the customer attempts to cancel, Then the system shall display the reason and prevent cancellation. | Negative
AC-011 | US-006 | Given an order is eligible for cancellation and the customer has already used a discount code, When the customer cancels the order, Then the system shall cancel the order and the discount code shall not be reissued (per policy). | Boundary
AC-012 | US-007 | Given an order is eligible for cancellation, When the customer selects "Cancel Order", Then the system shall display the refund amount, including any deductions for shipping or processing fees. | Positive
AC-013 | US-007 | Given an order is eligible for cancellation but the refund amount is $0, When the customer selects "Cancel Order", Then the system shall display: "This item is non-refundable. Cancellation will not result in a refund." | Negative
AC-014 | US-008 | Given the customer has selected a modification action, When the customer clicks "Confirm Change", Then the system shall display a confirmation dialog summarizing the change. | Positive
AC-015 | US-008 | Given the customer has selected a modification action, When the customer clicks "Cancel" in the confirmation dialog, Then the system shall return to the order details page without making changes. | Negative
AC-016 | US-009 | Given a modification or cancellation is successfully processed, When the processing is complete, Then the system shall send an email to the customer's registered email address within 5 minutes. | Positive
AC-017 | US-009 | Given a modification or cancellation fails, When the failure occurs, Then the system shall send an email to the customer explaining the failure and next steps. | Negative
AC-018 | US-012 | Given a modification is successfully processed, When the customer views the order details page, Then the system shall display the updated order information (e.g., new address, new shipping speed). | Positive
AC-019 | US-021 | Given a customer initiates a modification request, When the system evaluates eligibility, Then the system shall check order status, fulfillment stage, and business rules in real-time. | Positive
AC-020 | US-021 | Given the eligibility service is unavailable, When the customer initiates a modification request, Then the system shall display: "We are unable to process your request at this time. Please try again later or contact support." | Negative
AC-021 | US-022 | Given two modification requests are submitted for the same order simultaneously, When the system processes the requests, Then the first request shall be processed and the second shall be rejected with a message: "This order has already been modified. Please refresh and try again." | Positive

## Use Cases
UC ID | Name | Actor | Trigger | Preconditions | Main Flow | Alternative Flow | Exception Flow | Postconditions
UC-001 | View Order Eligibility | Customer | Customer navigates to order details page | Customer is logged in; order exists | 1. Customer navigates to order details. 2. System retrieves order status. 3. System evaluates eligibility. 4. System displays eligibility status and available actions. | 3a. Order is not eligible: System displays reason. | 2a. Order not found: System displays error. 3a. Eligibility service unavailable: System displays fallback message. | Customer sees eligibility status and available actions.
UC-002 | Modify Delivery Address | Customer | Customer selects "Modify Address" | Order is eligible for address modification; customer is logged in | 1. Customer selects "Modify Address." 2. System displays address form. 3. Customer enters new address. 4. System validates address. 5. Customer confirms. 6. System updates OMS. 7. System sends confirmation. | 4a. Address invalid: System displays validation error. 5a. Customer cancels: System returns to order details. | 6a. OMS update fails: System displays error and logs issue. | Delivery address updated; customer notified.
UC-003 | Change Shipping Speed | Customer | Customer selects "Change Shipping Speed" | Order is eligible for shipping speed change; customer is logged in | 1. Customer selects "Change Shipping Speed." 2. System displays available options with costs. 3. Customer selects new speed. 4. System calculates price difference. 5. Customer confirms. 6. System processes payment adjustment (if applicable). 7. System updates OMS. 8. System sends confirmation. | 4a. Price difference is $0: No payment adjustment. | 6a. Payment adjustment fails: System displays error and does not process change. | Shipping speed updated; payment adjusted; customer notified.
UC-004 | Cancel Individual Item | Customer | Customer selects "Cancel" for a specific item | Order contains multiple items; at least one item is eligible for cancellation | 1. Customer selects "Cancel" for an item. 2. System validates item eligibility. 3. System displays refund amount for item. 4. Customer confirms. 5. System updates OMS. 6. System releases inventory for item. 7. System processes refund. 8. System sends confirmation. | 2a. Item not eligible: System displays reason. 4a. Customer cancels: System returns to order details. | 7a. Refund fails: System logs issue and notifies finance team. | Item cancelled; refund processed; inventory released; customer notified.
UC-005 | Cancel Entire Order | Customer | Customer selects "Cancel Order" | Order is eligible for cancellation | 1. Customer selects "Cancel Order." 2. System displays refund amount. 3. Customer confirms. 4. System cancels order in OMS. 5. System releases all inventory. 6. System processes refund. 7. System sends confirmation. | 2a. Refund amount is $0: System displays message. 3a. Customer cancels: System returns to order details. | 4a. OMS cancellation fails: System displays error. 6a. Refund fails: System logs issue. | Order cancelled; refund processed; inventory released; customer notified.
UC-006 | View Modification History (Support Agent) | Support Agent | Agent opens customer record | Agent is logged in; customer has modification history | 1. Agent opens customer record. 2. System displays list of self-service actions. 3. Agent selects an action to view details. 4. System displays audit trail. | 2a. No actions: System displays "No self-service actions." | None | Agent has context for support interaction.
UC-007 | Handle Exception Case | Support Agent | Customer contacts support for ineligible request | Agent is logged in; customer has an ineligible request | 1. Agent reviews order. 2. Agent explains ineligibility. 3. Agent offers alternatives (e.g., return after delivery). 4. Agent documents interaction. | 2a. Agent identifies system error: Agent escalates to technical team. | None | Customer informed; interaction documented.
UC-008 | Generate Operational Report | Support Manager | Manager requests report | Manager is logged in; data is available | 1. Manager selects report type. 2. System generates report. 3. Manager views/downloads report. | 2a. No data: System displays "No data available." | 2a. Report generation fails: System displays error. | Manager has report for analysis.

## MoSCoW Prioritization
MoSCoW | Phase | ID | Requirement | Reasoning
Must Have | Phase 1 | BR-001 | Self-service capability | Core value proposition
Must Have | Phase 1 | BR-002 | Codified eligibility rules | Ensures consistency
Must Have | Phase 1 | BR-003 | Real-time processing | Key differentiator
Must Have | Phase 1 | BR-004 | Inventory release | Operational efficiency
Must Have | Phase 1 | BR-005 | Payment adjustment | Financial accuracy
Must Have | Phase 1 | BR-006 | Automated notifications | Customer experience
Must Have | Phase 1 | BR-011 | Compliance | Legal requirement
Must Have | Phase 1 | FR-001 | Eligibility display | Entry point
Must Have | Phase 1 | FR-002 | Real-time eligibility evaluation | Core functionality
Must Have | Phase 1 | FR-003 | Ineligibility reason | Transparency
Must Have | Phase 1 | FR-004 | Address modification | High-demand feature
Must Have | Phase 1 | FR-007 | Full order cancellation | High-demand feature
Must Have | Phase 1 | FR-008 | Fee/refund display | Transparency
Must Have | Phase 1 | FR-009 | Confirmation | Error prevention
Must Have | Phase 1 | FR-010 | OMS update | Data integrity
Must Have | Phase 1 | FR-011 | Inventory release | Operational efficiency
Must Have | Phase 1 | FR-012 | Payment adjustment | Financial accuracy
Must Have | Phase 1 | FR-013 | Email confirmation | Customer communication
Must Have | Phase 1 | NFR-001 | Response time | Usability
Must Have | Phase 1 | NFR-002 | Processing time | Usability
Must Have | Phase 1 | NFR-004 | Availability | Reliability
Must Have | Phase 1 | NFR-005 | Encryption | Security
Must Have | Phase 1 | NFR-006 | PCI compliance | Legal
Must Have | Phase 1 | NFR-007 | Cross-platform | Accessibility
Must Have | Phase 1 | NFR-009 | Clear error messages | Usability
Should Have | Phase 2 | BR-007 | Audit trail | Compliance; dispute resolution
Should Have | Phase 2 | BR-008 | Support agent visibility | Exception handling
Should Have | Phase 2 | BR-009 | Operational reporting | Continuous improvement
Should Have | Phase 2 | BR-010 | Peak volume handling | Scalability
Should Have | Phase 2 | FR-005 | Shipping speed change | Additional flexibility
Should Have | Phase 2 | FR-006 | Item-level cancellation | Additional flexibility
Should Have | Phase 2 | FR-014 | SMS notification | Enhanced communication
Should Have | Phase 2 | FR-015 | Push notification | Enhanced communication
Should Have | Phase 2 | FR-016 | Audit logging | Compliance
Should Have | Phase 2 | FR-017 | Support agent dashboard | Exception handling
Should Have | Phase 2 | FR-018 | Operational reports | Management visibility
Should Have | Phase 2 | NFR-003 | Concurrency support | Scalability
Should Have | Phase 2 | NFR-008 | Accessibility | Inclusivity
Should Have | Phase 2 | NFR-010 | Error logging | Operational visibility
Could Have | Phase 3 | — | Partial quantity modification | Lower demand; complex
Could Have | Phase 3 | — | International order support | Phase 2 consideration
Could Have | Phase 3 | — | Real-time carrier interception | Technical limitations
Could Have | Phase 3 | — | AI-powered modification suggestions | Nice-to-have
Won't Have | Out of Scope | — | Returns and exchanges | Separate initiative
Won't Have | Out of Scope | — | Post-delivery modifications | Different process
Won't Have | Out of Scope | — | Subscription orders | Not applicable
Won't Have | Out of Scope | — | B2B/wholesale orders | Different rules
Won't Have | Out of Scope | — | Split shipment modifications | Complexity deferred

## Traceability Matrix
BR ID | FR ID | US ID | AC ID | UAT ID
BR-001 | FR-001 | US-001 | AC-001, AC-002, AC-003 | UAT-001, UAT-002
BR-001 | FR-002 | US-001 | AC-019, AC-020 | UAT-003
BR-001 | FR-003 | US-002 | AC-004, AC-005 | UAT-004
BR-001 | FR-004 | US-003 | AC-006, AC-007, AC-008 | UAT-005, UAT-006
BR-001 | FR-005 | US-004 | — | UAT-007
BR-001 | FR-006 | US-005 | — | UAT-008
BR-001 | FR-007 | US-006 | AC-009, AC-010, AC-011 | UAT-009, UAT-010
BR-005 | FR-008 | US-007 | AC-012, AC-013 | UAT-011
BR-001 | FR-009 | US-008 | AC-014, AC-015 | UAT-012
BR-002 | FR-010 | US-012 | AC-018 | UAT-013
BR-004 | FR-011 | US-005, US-006 | — | UAT-014
BR-005 | FR-012 | US-006 | — | UAT-015
BR-006 | FR-013 | US-009 | AC-016, AC-017 | UAT-016
BR-006 | FR-014 | US-010 | — | UAT-017
BR-006 | FR-015 | US-011 | — | UAT-018
BR-007 | FR-016 | US-014 | — | UAT-019
BR-008 | FR-017 | US-013 | — | UAT-020
BR-009 | FR-018 | US-016 | — | UAT-021
BR-010 | NFR-003 | US-022 | AC-021 | UAT-022
BR-011 | NFR-005, NFR-006 | — | — | UAT-023

## UAT Scenarios
Test ID | Requirement ID | Scenario | Preconditions | Test Steps | Expected Result | Priority
UAT-001 | FR-001, FR-002 | Eligible order displays modification options | Order is in "Processing" status; customer logged in | 1. Navigate to order details. 2. Observe buttons. | "Modify Order" and "Cancel Order" buttons displayed. | High
UAT-002 | FR-003 | Ineligible order displays reason | Order is "Shipped"; customer logged in | 1. Navigate to order details. 2. Attempt to modify. | Message displayed: "This order has already shipped and cannot be modified." | High
UAT-003 | FR-002 | Real-time eligibility evaluation | Order is in "Processing" status | 1. Initiate modification. 2. Observe system response. | Eligibility evaluated within 3 seconds. | High
UAT-004 | FR-003 | Ineligibility reason for cancellation | Order is "Shipped" | 1. Attempt to cancel. 2. Observe message. | Reason displayed: "This order has already shipped." | High
UAT-005 | FR-004 | Modify delivery address | Order eligible; customer logged in | 1. Select "Modify Address." 2. Enter new valid address. 3. Confirm. | Address updated in OMS; confirmation displayed. | High
UAT-006 | FR-004 | Invalid address validation | Order eligible | 1. Select "Modify Address." 2. Enter invalid ZIP. 3. Submit. | Validation error displayed; submission prevented. | High
UAT-007 | FR-005 | Change shipping speed | Order eligible | 1. Select "Change Shipping Speed." 2. Select Express. 3. Confirm. | Shipping speed updated; price difference processed. | Medium
UAT-008 | FR-006 | Cancel individual item | Order with multiple items; one eligible | 1. Select "Cancel" for eligible item. 2. Confirm. | Item cancelled; refund processed; inventory released. | Medium
UAT-009 | FR-007 | Cancel entire order | Order eligible | 1. Select "Cancel Order." 2. Confirm. | Order cancelled; full refund processed; inventory released. | High
UAT-010 | FR-007 | Cancel ineligible order | Order "Shipped" | 1. Attempt to cancel. 2. Observe. | Cancellation prevented; reason displayed. | High
UAT-011 | FR-008 | Display refund amount | Order eligible | 1. Select "Cancel Order." 2. Observe refund display. | Refund amount displayed correctly. | High
UAT-012 | FR-009 | Confirmation required | Order eligible | 1. Select "Cancel Order." 2. Do not confirm. | No action taken until confirmation. | High
UAT-013 | FR-010 | OMS update | Order eligible | 1. Cancel order. 2. Check OMS. | OMS updated with cancellation. | High
UAT-014 | FR-011 | Inventory release | Order eligible | 1. Cancel order. 2. Check WMS. | Inventory released for cancelled items. | High
UAT-015 | FR-012 | Refund processing | Order eligible | 1. Cancel order. 2. Check payment gateway. | Refund initiated. | High
UAT-016 | FR-013 | Email confirmation | Order eligible | 1. Cancel order. 2. Check email. | Confirmation email received within 5 minutes. | High
UAT-017 | FR-014 | SMS notification | Customer opted in | 1. Cancel order. 2. Check SMS. | SMS received. | Medium
UAT-018 | FR-015 | Push notification | App installed | 1. Cancel order. 2. Check push. | Push notification received. | Medium
UAT-019 | FR-016 | Audit log | Order eligible | 1. Cancel order. 2. Check audit log. | Action logged with timestamp, user, action, before/after. | Medium
UAT-020 | FR-017 | Support agent view | Agent logged in | 1. Open customer record. 2. View self-service actions. | Actions visible. | Medium
UAT-021 | FR-018 | Operational report | Data available | 1. Generate report. 2. View metrics. | Report generated with accurate data. | Medium
UAT-022 | NFR-003 | Concurrent requests | 500 concurrent users | 1. Simulate 500 concurrent requests. 2. Monitor performance. | System handles without degradation. | Medium
UAT-023 | NFR-005, NFR-006 | Security compliance | System deployed | 1. Verify TLS. 2. Verify encryption at rest. 3. Verify PCI compliance. | All security requirements met. | High
UAT-024 | EC-001 | Duplicate request | Order eligible | 1. Click "Confirm" twice rapidly. | First request processed; second rejected with message. | High
UAT-025 | EC-005 | Service unavailable | Eligibility service down | 1. Attempt modification. 2. Observe. | Error message displayed; retry option available. | High
UAT-026 | EC-008 | Partial failure | Refund fails after OMS update | 1. Cancel order. 2. Simulate refund failure. | Order cancelled; refund pending; finance notified. | High
UAT-027 | EC-009 | Stale data | Order status changes during modification | 1. Initiate modification. 2. Change order status externally. 3. Confirm. | System re-validates; rejects if ineligible. | High
UAT-028 | EC-014 | Partial order eligibility | Some items eligible, some not | 1. Attempt to cancel ineligible item. | Only eligible items can be cancelled; message displayed. | High
UAT-029 | EC-021 | Order in picking stage | Order being picked | 1. Attempt to modify. | Modification prevented; message displayed. | High
UAT-030 | EC-024 | Session timeout | Session expires during modification | 1. Start modification. 2. Wait for session timeout. 3. Attempt to confirm. | Redirected to login; after login, can retry. | Medium

## Risk Register
Risk ID | Risk | Likelihood | Impact | Score | Mitigation | Owner
RISK-001 | OMS API does not support real-time queries | Medium | High | High | Technical spike early; fallback to cached data | Engineering Lead
RISK-002 | WMS integration is complex | Medium | High | High | Engage WMS vendor early; phased rollout | Engineering Lead
RISK-003 | Business rules are more complex than anticipated | High | Medium | High | Thorough requirements workshops; iterative rule definition | Product Manager
RISK-004 | Customers do not adopt self-service | Medium | Medium | Medium | UX testing; marketing; incentives | Product Manager
RISK-005 | Support team resistance to change | Medium | Medium | Medium | Change management; training; clear communication | Support Manager
RISK-006 | Peak volume exceeds capacity | Low | High | Medium | Load testing; auto-scaling; rate limiting | Engineering Lead
RISK-007 | Refund errors cause financial discrepancies | Low | High | Medium | Automated validation; finance review; audit trail | Finance Manager
RISK-008 | Compliance requirements change | Low | Medium | Low | Regular legal review; flexible design | Legal
RISK-009 | Integration failures cause poor customer experience | Medium | High | High | Graceful degradation; retry logic; clear error messages | Engineering Lead
RISK-010 | Scope creep delays launch | High | Medium | High | Strict scope control; MoSCoW prioritization | Product Manager

## Assumptions & Dependencies
ID | Type | Description | Impact if Invalid / Risk if Unavailable | Owner / Validation
AS-001 | Assumption | OMS provides real-time order status via API | Eligibility checks would be delayed or inaccurate | Technical spike; API contract review
AS-002 | Assumption | WMS can accept inventory release commands via API | Manual inventory release required | Technical spike; WMS vendor confirmation
AS-003 | Assumption | Payment gateway supports partial refunds | Full refunds only; reduced flexibility | Stripe documentation review
AS-004 | Assumption | Customers have access to web or mobile app | Some customers cannot self-serve | Analytics review; customer survey
AS-005 | Assumption | Business rules for eligibility are stable | Frequent rule changes require agile configuration | Stakeholder interviews; rule documentation
AS-006 | Assumption | Support team will adopt new exception-handling process | Support may continue handling all requests | Training plan; change management
AS-007 | Assumption | Peak volume is 3x normal | System may not handle unexpected spikes | Load testing; capacity planning
AS-008 | Assumption | Email/SMS delivery rates are acceptable | Customers may not receive notifications | Vendor SLA review
AS-009 | Assumption | Legal/Compliance requirements are understood | Compliance risk | Legal review
AS-010 | Assumption | No major changes to order lifecycle during implementation | Requirements may become outdated | Regular stakeholder check-ins
DEP-001 | Dependency | OMS API for real-time order status | Engineering | Cannot evaluate eligibility
DEP-002 | Dependency | WMS API for inventory release | Engineering | Inventory not released automatically
DEP-003 | Dependency | Stripe API for refunds | Engineering | Refunds not automated
DEP-004 | Dependency | Notification service (email/SMS/push) | Engineering | Customers not notified
DEP-005 | Dependency | UX design for portal/app interfaces | UX Designer | Cannot build UI
DEP-006 | Dependency | Business rules documentation | Product Manager | Cannot codify eligibility
DEP-007 | Dependency | QA environment with test data | QA Lead | Cannot test
DEP-008 | Dependency | Support team training | Support Manager | Poor exception handling
DEP-009 | Dependency | Legal/Compliance sign-off | Legal | Cannot launch
DEP-010 | Dependency | Analytics instrumentation | Data Team | Cannot measure KPIs

## KPI Success Metrics
KPI ID | KPI | Definition | Baseline (Simulated) | Target (Proposed) | Measurement Method
KPI-001 | Self-Service Adoption Rate | % of eligible modification/cancellation requests handled via self-service | 0% | 60% | Analytics tracking
KPI-002 | Support Contact Reduction | % reduction in support contacts related to order changes | 0% | 40% | CRM data
KPI-003 | Customer Satisfaction (CSAT) | Average CSAT for order change experience | 3.2/5 | 4.2/5 | Post-interaction survey
KPI-004 | Processing Time | Average time to complete modification/cancellation | 10 minutes | < 2 minutes | System logs
KPI-005 | Unnecessary Shipments | % of orders shipped despite cancellation request | 8% | 4% | OMS/WMS data
KPI-006 | Refund Processing Time | Average time for refund to be initiated | 24+ hours | < 1 hour | Payment gateway data
KPI-007 | Feature Error Rate | % of self-service requests resulting in errors | — | < 2% | System logs
KPI-008 | System Availability | % uptime for feature | — | 99.9% | Monitoring
KPI-009 | Notification Delivery Rate | % of notifications successfully delivered | — | > 98% | Notification service logs
KPI-010 | Support Agent Efficiency | Average handling time for exception cases | — | < 5 minutes | CRM data
KPI-011 | Customer Retention | % of customers who make another purchase after using feature | — | > 70% | Analytics
KPI-012 | Revenue Impact | Net revenue impact from reduced cancellations | — | Positive | Financial analysis